## ATP NEW
ACCEPTANCE TEST PROTOCOL
BPPT E-Learning System
No | FEATURES / FUNCTION | DESCRIPTION | TARGET |  |  | Status | Test Result | Note
|  |  | DAY | START | END
1 | Prepare Design Appwork (Backend) |  | 3 | 2020-10-19 | 2020-12-21
2 | Landing Page |  | 3 | 2020-10-22 | 2020-10-26
2.1 Design
2.2 Build CMS
2.2.1 Post Management
2.2.2 Page Management
2.2.3 Administration Content Management
2.3 Implementation (Design & CMS)
3 | Authentication |  | 2 | 2020-10-27 | 2020-10-28
3.1 Login
3.2 Logout
3.3 Register/Signup
4 | Data Master |  | 3 | 2020-10-29 | 2020-11-02
4.1 User Management
4.1.1 List/View
4.1.2 Create
4.1.3 Edit
4.1.4 Delete
4.1.5 Change Level
4.1.6 Change Activation
4.1.7 Change Profile
4.2 Grades Management
4.2.1 Create
4.2.2.Edit
4.2.3 Delete
4.2.4 View Detail
5 | LMS (Customized Module) |  | 17 | 2020-11-03 | 2020-11-25
5.1 Program Kegiatan
5.1.1 Create
5.1.2.Edit
5.1.3 Delete
5.1.4 View Detail
5.2 Mata Pelatihan
5.2.1 Create
5.2.1.1 Deskripsi, Tujuan (artikel, gambar, video)
5.2.1.2 Upload File (Attachment)
5.2.1.2 Pengajar
5.2.2.Edit
5.2.3 Delete
5.2.4 View Detail
5.3 Materi Pelatihan
5.3.1 Create
5.3.2.Edit
5.3.3 Delete
5.3.4 View Detail
5.4 Modul/Bahan Pelatihan
5.4.1 Discussion Forum
5.4.1.1 Create
5.4.1.2 Edit
5.4.1.3 Delete
5.4.1.4 View Detail
5.4.2 Dokumen (PDF/PPT)
5.4.2.1 Create
5.4.2.2 Edit
5.4.2.3 Delete
5.4.2.4 View Detail
5.4.3 Link Room Video Converence
5.4.2.1 Create
5.4.2.2 Edit
5.4.2.3 Delete
5.4.2.4 View Detail
5.4.4 Post Test/Pre Test
5.4.4.1 Create
5.4.4.2 Edit
5.4.4.3 Delete
5.4.4.4 View Detail
5.5 Kalender DIKLAT
5.5.1 Create Event
5.5.2 Edit Event
5.5.3 Delete Event
5.5.4 Calender Board View
5.5.5 Google Calender Integration
5.6 Evaluasi
5.6.1 Pengajar/Instruktur
5.6.2 Penyelenggara
5.6.3 Hasil Pelatihan
6 | Kemitraan |  | 2 | 2020-11-26 | 2020-11-27
6.1 Instansi/Unit Kerja/Perusahaan
6.1.1 Manajemen Program Kegiatan
6.1.2 Manajemen Mata Pelatihan
6.1.3 Manajemen Materi Pelatihan
6.1.4 Manajemen Content Pelatihan (Modul/Bahan)
6.1.5 Manajemen Peserta Pelatihan (Student)
6.1.6 Manajemen Pengajar (Instruktur)
7 | Bank Data |  | 2 | 2020-11-30 | 2020-12-01
7.1 Create
7.2 Edit
7.3 Delete
7.4 View Detail
8 | Sertifikasi |  | 2 | 2020-12-02 | 2020-12-03
8.1 Create
8.2 Edit
8.3 Delete
8.4 View Detail
9 | SCORM |  | 10 | 2020-12-04 | 2020-12-17
9.1 Running File Scorm (Compliant File)
9.2 Mengelola Data / Informasi (Compliant File)
9.2.1 Score
9.2.2 Completion Status
9.2.3 Bookmarking
9.3 Import (Compliant Package)
9.5 Another SCORM Standard
10 | Announcement |  | 2 | 2020-12-18 | 2020-12-21
10.1 Create Announcement
10.2 Edit Announcement
10.3 Lihat Announcement
10.4 Delete Announcement
11 | Statistik Dan Log Aktivitas |  | 2 | 2020-12-22 | 2020-12-23
11.1 Statistik
11.1.1 Statistik Page Hits
11.1.2 Statistik Students Per Course
11.1.3 Statistik Average Score Students Per Test
11.1.4 Other (Conditional/Request)
11.2 Log
11.2.1 Log Login
11.2.2 Log Move Pages
11.2.3 Log Content Activity
11.2.4 Log View
12 | Reporting |  | 2 | 2020-12-24 | 2020-12-25
12.1 Competency Breakdown
12.2 Activity Report
12.3 Course Participation
12.4 Activity completion
13 | Commentary & Review |  | 2 | 2020-12-28 | 2020-12-29
13.1 Modul/Bahan Pelatihan
13.2 Announcement
14 | Supporting Features |  | 2 | 2020-12-30 | 2020-12-31
14.1 Annotation
14.2 Rating (student feedback)
14.3 Badges
14.4 Learning Journey & Competencies
Total Day (*work day) |  |  | 54
Total Task |  |  | 131
Task Done |  |  | 0
Persentase |  |  | 0%
Target Selesai Tanggal |  |  | 2020-12-31
Note:
Pengerjaan bisa lebih cepat atau lambat tergantung dari situasi dan kondisi